### Program Development Simplified Project Plan

Purpose: This planning tool provides a detailed timeline and checklist to support districts in designing, implementing, and monitoring a high-impact tutoring program. Use this resource to guide each phase, from recruitment to evaluation, tailoring the plan to meet your district's unique needs and priorities.

Model Design | Begin before annual budget season; complete before budget finalized

  - Determine your model design elements.

  - Create guidance for selecting students/tutors.

  - Select new or existing High-Quality Instructional Materials.

  - Develop a Performance Management Plan.

Tutor Workforce | Begin during the semester prior to launching a build your own program, ideally after budget is finalized

Tutor Recruitment | Begin during the semester prior to launching a build your own program

  - Set a hiring window with deadlines.

  - Write and publish the tutor job description.

  - Advertise job postings to speed up the timeline.

  - Start designing tutor training to fill all gaps between “eligible applicant” and “ideal tutor.”

Tutor Selection | Complete prior to the end of the semester prior to launch

  - Determine and prioritize selection criteria.

  - Identify indicators of selection criteria.

  - Conduct interviews/model lessons/etc.

  - Analyze indicators and choose candidates.

Tutor Hiring |  Complete prior to tutor training launch

  - Draft tutor contracts and make job offers.

  - Process HR, payroll, background checks, etc.

  - Follow district policies for fingerprinting, etc.

Tutor Training | Complete prior to first tutor sessions

  - Adjust training based on tutor skill levels.

  - Provide all necessary preservice training. Summer school programming can also provide the opportunity to train tutors and begin tutoring while they tutor summer school students.

Implementation Phase

- School Selection Phase | Finalize when beginning of year (BOY) assessment data is available

  - Meet with schools and network chiefs to introduce the program.

  - Identify which schools and students will receive tutoring and why.

  - Roster students and finalize tutors

  - Communicate new partnerships with school community stakeholders (faculty, students, and caregivers).

- School Logistics Phase | Finalize in the first month of program launch

  - Establish backup days, times, and locations for tutoring in case the regular schedule is disrupted.

  - Meet with department heads to refine which students will work with tutors.

  - Meet with teachers’ union representatives to determine a compensation structure for teacher support.

  - Provide compensated onboarding sessions to introduce the tutoring program to key teachers.

  - Choose a primary point of contact at each school and establish the role's responsibilities.

  - Designate a caregiver liaison as the primary point of contact for caregivers with questions about tutoring.

- Tutor Logistics Phase | Start in the summer, complete by early in the semester prior to launch

  - Arrange for tutors to attend summer PD days to get to know teachers and observe school culture.

  - Set up school email/productivity suite accounts for tutors and get access to all necessary student data.

  - Arrange for tutors to gain access to teacher curriculum and lesson planning materials ahead of time.

  - Delineate responsibilities for absences: Who does what if a student is absent? If a tutor is absent?

  - Establish workflow for school leaders to sign off on tutor timesheets.

Continuous Improvement Phase | (Ongoing) Minimally bi-weekly after the first 6 weeks, increase as needed for school sites not meeting attendance thresholds throughout

programming.

  - Plan and schedule regular in-service training sessions to build tutors’ pedagogical skills.

  - Provide in-service training and coaching for each of your tutors.

  - Incentivize tutors to chaperone school trips/activities to integrate into school culture.

  - Schedule routine check-ins, professional development days, and professional learning communities.

  - Regular post-assessments will be conducted to measure student academic progress as the program scales.

  - Collect qualitative stakeholder feedback via surveys, focus groups, interviews, etc., at planned intervals.

  - Establish routine data reviews to monitor the impact per tutor, per school, and for the program as a whole.

Draft and present reports to relevant district authorities (i.e., School Board) to illustrate

program impact.